## Slide 1
14-Week Program Timeline
August 31 – December 4, 2026 · Beem Visa Debit Compliance Readiness
SEP
OCT
NOV
DEC
W1
W2
W3
W4
W5
W6
W7
W8
W9
W10
W11
W12
W13
W14
Operating Model & SOPs
Analytics Detection
DataVisor Requirements
Everlink → DataVisor Roadmap
Fraud Reporting Framework
Fraud
AML Framework Review
AML Monitoring Build
AML Reporting Framework
AML
Target-State Design
Current-State Compare
Finalize SOPs
Dispute Resolution
TPRM Process Review
Annual Attestation (ICICI)
Artifact Repository
TPRM & Oversight
Notes: TPRM & Oversight activities intentionally begin Oct/Nov, sequenced behind Fraud and AML priorities. Analytics and reporting-framework activities are scheduled in later weeks once core operating models are defined. ◆ = invoice milestone

## Slide 2
Fraud
End-to-end fraud investigation operating model, reporting framework, analytics, and Everlink → DataVisor transition
Activity | Docs Needed / Next Steps | Owner
Design & document fraud investigation operating model & SOPs (workflows, decisioning, escalation, disposition, transaction review, first-party fraud governance) across eDetect & eAuthenticate | Beem: Fraud policies and procedures; current-state fraud workflows/SOPs; Everlink eDetect & eAuthenticate documentation Deloitte: Lead operating model design and SOP drafting | Joint
Design & implement internal fraud reporting framework (loss reporting, Visa threshold monitoring, management reporting, Sponsor Bank & Visa reporting) | Beem: Existing fraud reports/dashboards; current reporting cadence and formats Deloitte: Design reporting framework and templates | Joint
Develop analytics-driven fraud detection process to identify emerging trends/anomalies from authentication failure patterns (Net New) | Deloitte: Design net-new analytics process; no existing Beem documentation required | Deloitte
Design DataVisor Visa Debit fraud monitoring requirements (data integration architecture, monitoring use cases, detection rules, governance) | Beem: Schedule stakeholder session with Tech/Architecture to confirm data source (DNA vs. Everlink); provide current DataVisor architecture/design documentation Deloitte: Lead requirements design once data source is confirmed | Joint
Develop Everlink → DataVisor transition roadmap (data integration, sequencing, testing, cutover, risk mitigation, governance) | Deloitte: No additional documentation identified; dependent on completion of DataVisor requirements | Deloitte
Beem
Deloitte
Joint

## Slide 3
AML
AML framework enhancement, internal reporting, and monitoring framework build for Visa Debit activity
Activity | Docs Needed / Next Steps | Owner
Review & enhance AML framework for Visa Debit (policies, procedures, governance controls, sanctions screening, investigation processes, regulatory/Sponsor Bank/Visa reporting obligations) | Beem: Current AML program documentation (investigation process, SOPs, policies); current reporting examples Deloitte: Connect with SME (potentially Navaera) to discuss PCI workaround | Joint
Design & implement internal AML reporting framework (operational and analytics performance reports) | Beem: Share current AML reporting format and output Deloitte: Design reporting framework | Joint
Design, build & operationalize AML monitoring framework for Visa Debit activity (methodologies, rules, alert scenarios, testing, production readiness) | Beem: Connect with Navaera to assess whether existing workaround meets requirements Deloitte: If Navaera workaround is insufficient, lead monitoring framework build | Joint
Beem
Deloitte
Joint

## Slide 4
Fraud & Non-Fraud Dispute Resolution
End-to-end dispute management lifecycle: target-state design, current-state comparison, and finalized SOPs
Activity | Docs Needed / Next Steps | Owner
Design target-state, end-to-end dispute management lifecycle (intake, fraud/non-fraud determination, provisional credit, chargeback submission via Central 1, Visa dispute processing, funds recovery) | Deloitte: Design target-state process first, ahead of current-state comparison | Deloitte
Compare target-state design against Beem's current-state dispute process to identify gaps | Deloitte: Complete gap analysis once target-state design is finalized | Deloitte
Finalize end-to-end dispute SOPs, process maps, and operational controls | Beem: Jesse (Fraud Disputes Owner) and Pattie to work through all dispute processes and investigation workflows with Deloitte | Joint
Beem
Deloitte
Joint

## Slide 5
TPRM & Oversight
Third-party risk management enhancement, annual attestation process, and centralized oversight repository
Activity | Docs Needed / Next Steps | Owner
Review & enhance existing TPRM processes to incorporate Visa Debit and BIN Sponsorship requirements | Beem: Current TPRM process documentation Deloitte: Review and enhance against Visa/BIN Sponsor requirements | Joint
Establish process to submit annual Attestation of Compliance to ICICI Bank | Deloitte: Design and document submission process (requirements TBD with Beem) | Deloitte
Design & implement centralized artifact repository and communication framework (policies, procedures, reporting artifacts, compliance evidence, governance docs, issue logs, correspondence) | Deloitte: Design repository structure and communication framework | Deloitte
Beem
Deloitte
Joint