Deloitte LLP

Bay Adelaide East

8 Adelaide Street West

Suite 200

Toronto ON M5H 0A9 Canada

Tel: 416-601-6150

Fax: 416-601-6151

www.deloitte.ca

August 27, 2026

Private and confidential

Pattie Lamboo

Vice President of Compliance

Beem Credit Union

300-678 Bernard Ave,

Kelowna, BC V1Y 6P3

Subject: Change Request – Visa Debit Issuing Compliance Readiness Support

This letter, effective August 31, 2026, outlines additional services that will be provided to Beem Credit Union (the “Client”, “Beem” or “you”) in accordance with the letter between Deloitte LLP and Client dated July 14, 2026 (the “Engagement Letter”).  Capitalized terms used herein and not defined shall have the meanings assigned to such terms in the Engagement Letter.  These additional services (as described below) shall be subject to the terms and conditions of the Engagement Letter, except as set forth below:

# Scope of Additional Services

We expect that our additional services may include, but not be limited to, supporting the launch of Visa Debit program across Fraud, AML, Fraud & Non-Fraud Dispute Resolution, TPRM, and Oversight functions. The specific additional services to be performed by us (collectively, the “Additional Services”) will be established based on discussions with you as additional information is obtained during the course of the engagement.  Based upon our discussions with you to date, our initial understanding of the Additional Services you have requested us to perform, and we have agreed to perform are summarized as follows:

| Compliance Theme | Activities | Ref. Visa Rule |
| --- | --- | --- |
| Fraud | - Design and document the end-to-end debit card fraud investigation operating model, including investigation workflows, decisioning criteria, escalation paths, alert disposition procedures, transaction review processes, and Visa’s first-party fraud governance. Deliver comprehensive Standard Operating Procedures (SOPs), process documentation, and investigator guidance materials to support ongoing fraud operations, across Everlink eDetect and eAuthenticate platforms. | - Ref: 10.4.7.1, 1.9.4.3, 10.4.7.3 |
|  | - Design and implement an internal fraud reporting framework, including fraud loss reporting, Visa threshold monitoring, management reporting, and Sponsor Bank and Visa reporting processes. |  |
|  | - Develop an analytics-driven fraud detection process to identify emerging fraud trends and anomalies based on authentication failure patterns. |  |
|  | - Design DataVisor Visa debit fraud monitoring requirements, including data integration architecture, monitoring use cases, fraud detection rules, and governance considerations. | - N/A |
|  | - Develop a comprehensive integration and transition roadmap for the migration of fraud monitoring capabilities from Everlink to DataVisor following Visa Debit launch. The roadmap will include data integration requirements, operating model impacts, implementation sequencing, testing and validation activities, cutover considerations, risk mitigation strategies, and transition governance to support a seamless migration to the future-state platform. | - N/A |
| AML | - Review and enhance the AML framework to support Visa Debit products and services, including policies, procedures, governance controls, sanctions screening requirements, investigation processes, regulatory, Sponsor Bank and Visa reporting obligations. | - Ref: 1.9.1.7, 1.9.1.8, 1.1.1.15, 1.1.1.3 |
|  | - Design and implement an internal AML reporting framework, including operational and analytics performance reports. |  |
|  | - Design, build and operationalize the AML monitoring framework for Visa Debit activity, including monitoring methodologies, monitoring rules, alert scenarios, testing, and production readiness activities. |  |
| Fraud & Non-Fraud Dispute Resolution | - Design and document the end-to-end dispute management lifecycle, including dispute intake, fraud or non-fraud determination, provisional credit issuance (see out of scope activity #1), chargeback submission (via Central 1), Visa dispute processing, and funds recovery activities. Deliver supporting procedures, process maps, and operational controls to support efficient dispute resolution and recovery operations. | - Ref: 11.1, 11.2, 11.3, 11.4, 11.6, 4.1.11, 1.10.1.1, 11.11, 11.12, 11.13, 11.7, 11.3.1 |
| TPRM & Oversight | - Review and enhance existing third-party risk management processes to incorporate Visa Debit and BIN Sponsorship requirements, ensuring vendor oversight activities align with applicable regulatory, network, and contractual obligations. | - 10.2.2.5, 10.2.2.6 |
|  | - Establish process to submit annual Attestation of Compliance to ICICI Bank. | - N/A |
|  | - Design and implement a centralized artifact repository and communication framework to support Visa Debit oversight activities, including storage and management of policies, procedures, reporting artifacts, compliance evidence, governance documentation, issue logs, and correspondence with regulators, Visa, and 3rd parties | - N/A |

Out of scope activities:

- The provisional credit issuance process will not include the modification of the existing accounting, general ledger (GL), reconciliation, or financial posting mechanisms. Any modification required will be performed by Beem's Payments Operations and/or technology teams and are outside the scope of this Change Request.

- Custom software development, production system configuration beyond agreed implementation support activities, and vendor implementation services are outside the scope of this Change Request.

- The DataVisor workstream is limited to requirements definition, future-state design, integration planning, and transition planning. Execution of the migration, system build, vendor configuration, and production deployment activities are outside the scope of this Change Request.

Assumptions:

- Beem will designate business and technology stakeholders from Fraud, AML/Compliance, Card Operations, Information Security, Risk, and Technology to participate in workshops, provide information, and review deliverables in a timely manner.

- Beem and its third-party service providers (e.g., Everlink, Central 1, ICICI Bank, DataVisor) will make subject matter experts available as required to understand current-state processes, system capabilities, integration requirements, and compliance obligations.

- Required documentation regarding Everlink eDetect, eAuthenticate, Central 1 dispute processing, DataVisor, ICICI Bank sponsor requirements, and related third-party services will be made available to the project team in a timely manner.

- Stakeholder feedback on draft deliverables will be consolidated and provided within five (5) business days of submission unless otherwise agreed.

- Beem will provide access to relevant existing policies, procedures, process documentation, reporting templates, governance materials, system documentation, implementation plans, and other relevant artifacts.

- Beem will provide Deloitte with access to available transaction data, fraud data, dispute data, AML monitoring information, and reporting artifacts required to support process design and monitoring rule development.

- Any monitoring rules, fraud detection scenarios, AML thresholds, sanctions screening parameters, or reporting criteria produced during the engagement will be based on industry practices, available information, and Beem's risk appetite and will require Beem approval prior to implementation.

These Additional Services may be changed or modified by mutual agreement of the parties if, for example, unforeseen circumstances arise.  We will promptly discuss any such circumstances with you and, likewise, you agree to notify us promptly if modifications to the Additional Services are requested.

# Timing of Additional Services

The engagement will be conducted over a 14-week period, from August 31, 2026 through December 4, 2026.

# Fees

The standard fee for this engagement is CAD $435,000, plus out-of-pocket expenses and applicable taxes. Deloitte is providing a one-time investment of CAD $70,000 in support of Beem Credit Union's Visa Debit transformation initiative, resulting in a reduced engagement fee of CAD $365,000, plus out-of-pocket expenses and applicable taxes. This estimate is based on you fulfilling your responsibilities and on the accuracy of the Assumptions stated in this Change Request. Deloitte's invoices shall be issued in accordance with the payment schedule set out below.

| Services Price Terms |  |  |
| --- | --- | --- |
| Invoice | Invoice Date | Amount (CAD) |
| - Invoice #1 | September 25, 2026 | $165,000 |
| - Invoice #2 | October 30, 2026 | $100,000 |
| - Invoice #3 | December 4, 2026 | $100,000 |
| Total |  | $365,000 + tax |

# Other terms

If the above terms are acceptable to you and the Additional Services are in accordance with your understanding, please sign the copy of this letter in the space provided and return it to us.

We appreciate the opportunity to serve you, and we look forward to a continuing relationship.

Very truly yours,

DELOITTE LLP

Name: Kevin Luh

Title: Partner

Accepted and Agreed to this ____ day of __________, 20_:

Beem Credit Union

Name:				 Pattie Lamboo

Title:				 VP, Compliance