## Fraud
Fraud Workstream — Project Plan
Source: Phase 2 Kickoff Deck (Engagement Scope & Timelines / Activities Overview). Sub-activities are Deloitte's proposed breakdown.
# | Activity / Sub-Activity | Type | Owner | Point of Contact | Start Date | End Date | Notes | Status
1 | Design and Document Fraud Investigation Operating Model & Process | Activity | Deloitte | Jesse Y. | 2026-09-08 | 2026-10-18 |  | Not Started
| Collect current enterprise fraud policies & current fraud investigation/case management process | Sub-Activity | Beem | Jesse Y. | 2026-09-08 | 2026-09-10 | Due Thu Sept 10 EOD | Not Started
| Conduct working sessions on investigation workflows, decisioning criteria & escalation paths | Sub-Activity | Deloitte | Jesse Y. | 2026-09-15 | 2026-09-27 |  | Not Started
| Draft fraud investigation operating model & SOPs (incl. eDetect & eAuthenticate) | Sub-Activity | Deloitte | Jesse Y. | 2026-09-21 | 2026-10-11 |  | Not Started
| Review & finalize SOPs with Beem stakeholders | Sub-Activity | Joint | Jesse Y. | 2026-10-12 | 2026-10-18 |  | Not Started
2 | Design DataVisor Monitoring Requirements | Activity | Deloitte | DataVisor Product Owner (TBC) / Jesse Y. | 2026-09-21 | 2026-10-18 |  | Not Started
| Obtain DataVisor solution overview, design spec & current data flow/architecture diagrams | Sub-Activity | Beem | DataVisor Product Owner (TBC) | 2026-09-08 | 2026-09-10 | Due Thu Sept 10 EOD | Not Started
| Confirm data source (DNA vs. Everlink) with Tech/Architecture stakeholders | Sub-Activity | Joint | TBC | 2026-09-21 | 2026-09-27 |  | Not Started
| Draft monitoring use cases, detection rules & governance requirements | Sub-Activity | Deloitte | Jesse Y. | 2026-09-28 | 2026-10-11 |  | Not Started
| Review & finalize requirements document | Sub-Activity | Joint | Jesse Y. | 2026-10-12 | 2026-10-18 |  | Not Started
3 | Develop Everlink -> DataVisor Transition Roadmap | Activity | Deloitte | Shikhar / David / Cynthia (TBC); Manoj (technical) | 2026-10-19 | 2026-11-22 |  | Not Started
| Confirm technical specifications with Manoj | Sub-Activity | Joint | Manoj | 2026-10-19 | 2026-10-25 |  | Not Started
| Assess data integration requirements & operating model impacts | Sub-Activity | Deloitte | Shikhar/David/Cynthia (TBC) | 2026-10-19 | 2026-11-01 |  | Not Started
| Draft implementation sequencing, testing/validation & cutover plan | Sub-Activity | Deloitte | Shikhar/David/Cynthia (TBC) | 2026-11-02 | 2026-11-15 |  | Not Started
| Review & finalize roadmap with stakeholders | Sub-Activity | Joint | Shikhar/David/Cynthia (TBC) | 2026-11-16 | 2026-11-22 |  | Not Started
4 | Develop Analytics-driven Fraud Detection Process | Activity | Deloitte | Jesse Y. | 2026-11-09 | 2026-12-11 |  | Not Started
| Define authentication-failure-pattern analysis approach (net-new; no existing docs required) | Sub-Activity | Deloitte | Jesse Y. | 2026-11-09 | 2026-11-15 | N/A - net new | Not Started
| Draft analytics-driven detection methodology | Sub-Activity | Deloitte | Jesse Y. | 2026-11-16 | 2026-11-29 |  | Not Started
| Review & validate approach with Fraud team | Sub-Activity | Joint | Jesse Y. | 2026-11-30 | 2026-12-06 |  | Not Started
| Finalize process documentation | Sub-Activity | Deloitte | Jesse Y. | 2026-12-07 | 2026-12-11 |  | Not Started
5 | Update Fraud Reporting Process | Activity | Deloitte | Jesse Y. | 2026-11-23 | 2026-12-11 |  | Not Started
| Collect current fraud loss reporting/dashboards & reporting cadence/formats | Sub-Activity | Beem | Jesse Y. | 2026-11-23 | 2026-11-29 |  | Not Started
| Draft updated fraud reporting framework (loss reporting, VIMP thresholds, mgmt reporting, Sponsor Bank & Visa reporting) | Sub-Activity | Deloitte | Jesse Y. | 2026-11-23 | 2026-12-06 |  | Not Started
| Review & finalize with stakeholders | Sub-Activity | Joint | Jesse Y. | 2026-12-07 | 2026-12-11 |  | Not Started
| Completion of Fraud Transformation Activities | Milestone | Joint |  | 2026-12-07 | 2026-12-11 |  | Not Started

## AML
AML Workstream — Project Plan
Source: Phase 2 Kickoff Deck (Engagement Scope & Timelines / Activities Overview). Sub-activities are Deloitte's proposed breakdown.
# | Activity / Sub-Activity | Type | Owner | Point of Contact | Start Date | End Date | Notes | Status
6 | Review the Current AML Process and Policy | Activity | Deloitte | Sandra M. | 2026-09-08 | 2026-10-18 |  | Not Started
| Collect current AML policy & current AML alert, case, and regulatory reporting processes | Sub-Activity | Beem | Sandra M. | 2026-09-08 | 2026-09-10 | Due Thu Sept 10 EOD | Not Started
| Conduct working sessions with AML team | Sub-Activity | Deloitte | Sandra M. | 2026-09-15 | 2026-09-27 |  | Not Started
| Draft enhanced AML framework (policies, governance controls, sanctions screening, investigation processes) | Sub-Activity | Deloitte | Sandra M. | 2026-09-21 | 2026-10-11 |  | Not Started
| Review & finalize with Beem stakeholders | Sub-Activity | Joint | Sandra M. | 2026-10-12 | 2026-10-18 |  | Not Started
7 | Update the AML Monitoring Process | Activity | Deloitte | Sandra M.; Navaera Relationship Owner (TBC) | 2026-09-28 | 2026-11-15 |  | Not Started
| Beem to introduce Deloitte to Navaera to discuss PCI-compliance workaround | Sub-Activity | Beem | Sandra M. / Navaera Relationship Owner (TBC) | 2026-09-28 | 2026-10-04 | Blocking dependency | Not Started
| Assess whether Navaera's workaround is sufficient; confirm build approach | Sub-Activity | Joint | Sandra M. | 2026-10-05 | 2026-10-18 |  | Not Started
| Design monitoring methodologies, monitoring rules & alert scenarios | Sub-Activity | Deloitte | Sandra M. | 2026-10-12 | 2026-11-01 |  | Not Started
| Testing & production readiness activities | Sub-Activity | Deloitte | Sandra M. | 2026-11-02 | 2026-11-15 |  | Not Started
8 | Update AML Reporting Process | Activity | Deloitte | Sandra M. | 2026-11-09 | 2026-12-06 |  | Not Started
| Collect current AML reports/dashboards & reporting cadence/formats | Sub-Activity | Beem | Sandra M. | 2026-11-09 | 2026-11-15 |  | Not Started
| Draft internal AML reporting framework (operational & analytics performance reports) | Sub-Activity | Deloitte | Sandra M. | 2026-11-16 | 2026-11-29 |  | Not Started
| Review & finalize with stakeholders | Sub-Activity | Joint | Sandra M. | 2026-11-30 | 2026-12-06 |  | Not Started
| Completion of AML Transformation Activities | Milestone | Joint |  | 2026-11-30 | 2026-12-06 |  | Not Started

## Dispute Resolution
Dispute Resolution Workstream — Project Plan
Source: Phase 2 Kickoff Deck (Engagement Scope & Timelines / Activities Overview). Sub-activities are Deloitte's proposed breakdown.
# | Activity / Sub-Activity | Type | Owner | Point of Contact | Start Date | End Date | Notes | Status
9 | Build Target-state Dispute Management Process | Activity | Deloitte | Loni B. (Non-fraud Disputes); Pattie L. (Fraudulent Disputes) | 2026-09-08 | 2026-09-27 |  | Not Started
| Collect current dispute policies/process (incl. Central 1) & current dispute forms/templates/comms | Sub-Activity | Beem | Loni B. / Pattie L. | 2026-09-08 | 2026-09-10 | Due Thu Sept 10 EOD | Not Started
| Design target-state dispute lifecycle (intake, fraud/non-fraud determination, provisional credit, chargeback via Central 1, Visa processing, funds recovery) | Sub-Activity | Deloitte | Loni B. / Pattie L. | 2026-09-15 | 2026-09-20 |  | Not Started
| Draft supporting procedures & process maps | Sub-Activity | Deloitte | Loni B. / Pattie L. | 2026-09-21 | 2026-09-27 |  | Not Started
10 | Refine / Finalize Target-State Process | Activity | Joint | Loni B. (Non-fraud Disputes); Pattie L. (Fraudulent Disputes) | 2026-09-21 | 2026-12-11 |  | Not Started
| Compare target-state design against Beem's current-state dispute process | Sub-Activity | Deloitte | Loni B. / Pattie L. | 2026-09-21 | 2026-10-11 |  | Not Started
| Conduct review sessions with Loni B. and Pattie L. | Sub-Activity | Joint | Loni B. / Pattie L. | 2026-10-05 | 2026-11-29 | Ongoing | Not Started
| Incorporate feedback & refine process maps and operational controls | Sub-Activity | Deloitte | Loni B. / Pattie L. | 2026-10-12 | 2026-11-29 |  | Not Started
| Final sign-off on target-state dispute process | Sub-Activity | Joint | Loni B. / Pattie L. | 2026-12-07 | 2026-12-11 |  | Not Started
| Completion of Dispute Resolution Transformation Activities | Milestone | Joint |  | 2026-12-07 | 2026-12-11 |  | Not Started

## TPRM & Oversight
TPRM & Oversight Workstream — Project Plan
Source: Phase 2 Kickoff Deck (Engagement Scope & Timelines / Activities Overview). Sub-activities are Deloitte's proposed breakdown.
# | Activity / Sub-Activity | Type | Owner | Point of Contact | Start Date | End Date | Notes | Status
11 | Enhance Existing TPRM Process | Activity | Deloitte | Akinwale A. | 2026-11-02 | 2026-11-22 |  | Not Started
| Collect current TPRM policies & processes | Sub-Activity | Beem | Akinwale A. | 2026-11-02 | 2026-11-08 |  | Not Started
| Assess current process against Visa Debit & BIN Sponsorship requirements | Sub-Activity | Deloitte | Akinwale A. | 2026-11-02 | 2026-11-15 |  | Not Started
| Draft enhanced TPRM process & controls | Sub-Activity | Deloitte | Akinwale A. | 2026-11-09 | 2026-11-22 |  | Not Started
| Review & finalize with Akinwale A. | Sub-Activity | Joint | Akinwale A. | 2026-11-16 | 2026-11-22 |  | Not Started
12 | Establish ICICI Attestation Process | Activity | Deloitte | Akinwale A. | 2026-11-16 | 2026-12-06 |  | Not Started
| Collect excerpt of ICICI contract (attestation requirements, templates, submission guidance) | Sub-Activity | Beem | Akinwale A. | 2026-11-16 | 2026-11-22 |  | Not Started
| Draft annual Attestation of Compliance submission process | Sub-Activity | Deloitte | Akinwale A. | 2026-11-23 | 2026-11-29 |  | Not Started
| Review & finalize with Akinwale A. / Pattie L. | Sub-Activity | Joint | Akinwale A. | 2026-11-30 | 2026-12-06 |  | Not Started
13 | Build Centralized Artifact Repository | Activity | Deloitte | Akinwale A. | 2026-11-30 | 2026-12-11 |  | Not Started
| Design repository structure & communication framework | Sub-Activity | Deloitte | Akinwale A. | 2026-11-30 | 2026-12-06 | N/A - no doc needed | Not Started
| Configure & populate repository (policies, procedures, reporting artifacts, compliance evidence, governance docs, issue logs) | Sub-Activity | Deloitte | Akinwale A. | 2026-11-30 | 2026-12-11 |  | Not Started
| Review & hand over to Beem | Sub-Activity | Joint | Akinwale A. | 2026-12-07 | 2026-12-11 |  | Not Started
| Completion of TPRM & Oversight Transformation Activities | Milestone | Joint |  | 2026-12-07 | 2026-12-11 |  | Not Started

## Consolidated - High Level
Visa Debit Transformation Phase — Consolidated Project Plan
14-Week Engagement · Sept 8 – Dec 11, 2026 · High-level view across all workstreams (activity-level; see individual tabs for sub-activities)
Workstream | # | Activity | Owner | Point of Contact | Start Date | End Date | Status
All |  | Ongoing Project Management (Weekly Status Update) | Deloitte | Engagement Lead | 2026-09-08 | 2026-12-11 | Ongoing
Fraud | 1 | Design and Document Fraud Investigation Operating Model & Process | Deloitte | Jesse Y. | 2026-09-08 | 2026-10-18 | Not Started
Fraud | 2 | Design DataVisor Monitoring Requirements | Deloitte | DataVisor Product Owner (TBC) / Jesse Y. | 2026-09-21 | 2026-10-18 | Not Started
Fraud | 3 | Develop Everlink -> DataVisor Transition Roadmap | Deloitte | Shikhar / David / Cynthia (TBC); Manoj (technical) | 2026-10-19 | 2026-11-22 | Not Started
Fraud | 4 | Develop Analytics-driven Fraud Detection Process | Deloitte | Jesse Y. | 2026-11-09 | 2026-12-11 | Not Started
Fraud | 5 | Update Fraud Reporting Process | Deloitte | Jesse Y. | 2026-11-23 | 2026-12-11 | Not Started
Fraud |  | Completion of Fraud Transformation Activities | Joint |  | 2026-12-07 | 2026-12-11 | Not Started
AML | 6 | Review the Current AML Process and Policy | Deloitte | Sandra M. | 2026-09-08 | 2026-10-18 | Not Started
AML | 7 | Update the AML Monitoring Process | Deloitte | Sandra M.; Navaera Relationship Owner (TBC) | 2026-09-28 | 2026-11-15 | Not Started
AML | 8 | Update AML Reporting Process | Deloitte | Sandra M. | 2026-11-09 | 2026-12-06 | Not Started
AML |  | Completion of AML Transformation Activities | Joint |  | 2026-11-30 | 2026-12-06 | Not Started
Dispute Resolution | 9 | Build Target-state Dispute Management Process | Deloitte | Loni B. (Non-fraud Disputes); Pattie L. (Fraudulent Disputes) | 2026-09-08 | 2026-09-27 | Not Started
Dispute Resolution | 10 | Refine / Finalize Target-State Process | Joint | Loni B. (Non-fraud Disputes); Pattie L. (Fraudulent Disputes) | 2026-09-21 | 2026-12-11 | Not Started
Dispute Resolution |  | Completion of Dispute Resolution Transformation Activities | Joint |  | 2026-12-07 | 2026-12-11 | Not Started
TPRM & Oversight | 11 | Enhance Existing TPRM Process | Deloitte | Akinwale A. | 2026-11-02 | 2026-11-22 | Not Started
TPRM & Oversight | 12 | Establish ICICI Attestation Process | Deloitte | Akinwale A. | 2026-11-16 | 2026-12-06 | Not Started
TPRM & Oversight | 13 | Build Centralized Artifact Repository | Deloitte | Akinwale A. | 2026-11-30 | 2026-12-11 | Not Started
TPRM & Oversight |  | Completion of TPRM & Oversight Transformation Activities | Joint |  | 2026-12-07 | 2026-12-11 | Not Started