## Slide 1
September 8TH, 2026
Visa Debit Transformation Phase Support
Kickoff Meeting

## Slide 2
Align on project scope, stakeholder responsibilities, and key mobilization activities to support a successful project launch.
Today's Discussion Objectives
July
WE ARE HERE
Reviewed Visa's Issuing Debit Card Rules
2
Mid-December
4
1
3
Identified FTE needs and required changes for the compliance function
Visa Debit go-live
Assessed Beem's current-state compliance function (Across AML, fraud, fraudulent disputes, and TPRM & oversight)
Implementing the identified compliance program changes
(Expanded scope to also cover non-fraud dispute/chargeback readiness ahead of go-live)
Beem to hire new FTEs or retain existing FTEs as needed
September

## Slide 3
4
Align on project scope, stakeholder responsibilities, and key mobilization activities to support a successful project launch.
Today's Discussion Objectives
1
Walkthrough the engagement scope and timelines
2
Review required documentation and key artifacts
4
Schedule recurring project touchpoints and meeting cadence
5
Confirm access requirements (SharePoint, Confluence, Teams)
6
Confirm contracting and engagement letter execution
3
Confirm stakeholder involvement and day-to-day points of contact

## Slide 4
 | WEEK 1 Sept 8 | WEEK 2 Sept 15 | WEEK 3 Sep 21 | WEEK 4 Sep 28 | WEEK 5 Oct 5 | WEEK 6 Oct 12 | WEEK 7 Oct 19 | WEEK 8 Oct 26 | WEEK 9 Nov 2 | WEEK 10 Nov 9 | WEEK 11 Nov 16 | WEEK 12 Nov 23 | WEEK 13 Nov 30 | WEEK 14 Dec 7
Ongoing Project Management |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Legend:
Weekly Status Update
Deliverable
4
Fraud
3. Design DataVisor Monitoring Requirements
4. Develop Everlink -> DataVisor Transition Roadmap
1. Design and Document Fraud Investigation Operating Model & Process
2. Develop Analytics-driven Fraud Detection Process
5. Update Fraud Reporting Process
AML
6. Review the Current AML Process and Policy
7. Update the AML Monitoring Process
Update AML Reporting Process
Dispute Resolution
Build Target-state Dispute Management Process
Refine / Finalize Target-State Process
TPRM & Oversight
Enhance Existing TPRM Process
Establish ICICI Attestation Process
Build Centralized Artifact Repository
Completion of AML Transformation Activities
Completion of Dispute Resolution Transformation Activities
Completion of Fraud Transformation Activities
Completion of TPRM & Oversight Transformation Activities
Over the course of 14 weeks , Deloitte will support the transformation phase for the following compliance areas: Fraud, AML, Dispute Resolution, and TPRM & Oversight.
Engagement Scope and Timelines
  Out of Scope Activities
Changes to accounting, GL, reconciliation, and financial posting processes are out of scope.
Custom development, vendor implementation, and production configuration activities are out of scope.
The DataVisor workstream excludes system build, configuration, migration execution, and production deployment activities.
  Assumptions
Timely access to stakeholders and SMEs will be provided.
Required documentation and artifacts will be made available.
Feedback on deliverables will be provided within five (5) business days.
Access to relevant documentation, data, and reporting artifacts will be provided.
All proposed rules, thresholds, and reporting criteria will require Beem approval prior to implementation.

## Slide 5
Overview of the key fraud activities supporting Beem's Visa Debit program, including the activities, dependencies, and stakeholder engagement required for successful delivery.
Fraud Activities Overview
# | Activity | Description | Document Needed | Beem Point of Contact (TBC)
1 | Design and Document Fraud Investigation Operating Model & Process | Design and document the end-to-end debit card fraud investigation operating model, including investigation workflows, decisioning criteria, escalation paths, alert disposition procedures, transaction review processes, and Visa’s first-party fraud governance. Deliver comprehensive Standard Operating Procedures (SOPs), process documentation, and investigator guidance materials to support ongoing fraud operations, across Everlink eDetect and eAuthenticate platforms. | By Thursday Sept 10 EOD Current enterprise fraud policies Current fraud investigation and case management process | Jesse Y. To be confirmed
2 | Design DataVisor Monitoring Requirements | Design DataVisor Visa debit fraud monitoring requirements, including data integration architecture, monitoring use cases, fraud detection rules, and governance considerations. | By Thursday Sept 10 EOD DataVisor solution overview and design specification Current DataVisor transaction / data flows diagram, solution architecture, and integration diagram | DataVisor Product Owner To be confirmed
3 | Develop Everlink -> DataVisor Transition Roadmap | Develop a comprehensive integration and transition roadmap for the migration of fraud monitoring capabilities from Everlink to DataVisor following Visa Debit launch. The roadmap will include data integration requirements, operating model impacts, implementation sequencing, testing and validation activities, cutover considerations, risk mitigation strategies, and transition governance to support a seamless migration to the future-state platform. |  | Everlink Relationship Owner To be confirmed
4 | Develop Analytics-driven Fraud Detection Process | Develop an analytics-driven fraud detection process to identify emerging fraud trends and anomalies based on authentication failure patterns. | N / A - Design net-new analytics process; no existing Beem documentation required | Jesse Y. To be confirmed
5 | Update Fraud Reporting Process | Design and implement an internal fraud reporting framework, including fraud loss reporting, Visa threshold monitoring, management reporting, and Sponsor Bank and Visa reporting processes. | Current fraud loss reporting and/or dashboards Current fraud reporting process including cadence and reporting formats | Jesse Y. To be confirmed

## Slide 6
Overview of the key AML activities supporting Beem's Visa Debit program, including the activities, dependencies, and stakeholder engagement required for successful delivery.
AML Activities Overview
# | Activity | Description | Document Needed | Beem Point of Contact (TBC)
6 | Review the Current AML Process and Policy | Review and enhance the AML framework to support Visa Debit products and services, including policies, procedures, governance controls, sanctions screening requirements, investigation processes, regulatory, Sponsor Bank and Visa reporting obligations. | by Thursday Sept 10 EOD Current AML Policy Current AML alert, case and reg reporting processes | Sandra Makortoff To be confirmed
7 | Update the AML Monitoring Process | Design, build and operationalize the AML monitoring framework for Visa Debit activity, including monitoring methodologies, monitoring rules, alert scenarios, testing, and production readiness activities. | N/A –Navaera is not PCI compliant. First we need to talk to them to learn about the workaround. So beem needs to introduce us. | Sandra Makortoff To be confirmed Navaera Relationship Owner To be confirmed
8 | Update AML Reporting Process | Design and implement an internal AML reporting framework, including operational and analytics performance reports. | Current AML reports and/or dashboards Current AML reporting process including cadence and reporting formats | Sandra Makortoff To be confirmed

## Slide 7
Overview of the key dispute resolution activities supporting Beem's Visa Debit program, including the activities, dependencies, and stakeholder engagement required for successful delivery.
Dispute Resolution Activities Overview
# | Activity | Description | Document Needed | Beem Point of Contact (TBC)
9 | Build Target-state Dispute Management Process | Design and document the end-to-end dispute management lifecycle, including dispute intake, fraud or non-fraud determination, provisional credit issuance (see out of scope activity #1), chargeback submission (via Central 1), Visa dispute processing, and funds recovery activities. Deliver supporting procedures, process maps, and operational controls to support efficient dispute resolution and recovery operations. | Current dispute policies and process (i.e., dispute process via Central1) Current dispute forms, templates, and customer communications template | Jesse N. To be confirmed
10 | Refine / Finalize Target-State Process |  |  | 

## Slide 8
Overview of the key TPRM & Oversight activities supporting Beem's Visa Debit program, including the activities, dependencies, and stakeholder engagement required for successful delivery.
TPRM & Oversight Activities Overview
# | Activity | Description | Document Needed | Beem Point of Contact (TBC)
11 | Enhance Existing TPRM Process | Review and and enhance existing third-party risk management processes to incorporate Visa Debit and BIN Sponsorship requirements, ensuring vendor oversight activities align with applicable regulatory, network, and contractual obligations.. | Current TPRM policies and processes | TPRM Team Lead To be confirmed
12 | Establish ICICI Attestation Process | Establish process to submit annual Attestation of Compliance to ICICI Bank. | Excerpt of the ICICI contract showing the attestation requirements, templates, and submission guidance | Pattie L. To be confirmed
13 | Build Centralized Artifact Repository | Design and implement a centralized artifact repository and communication framework to support Visa Debit oversight activities, including storage and management of policies, procedures, reporting artifacts, compliance evidence, governance documentation, issue logs, and correspondence with regulators, Visa, and 3rd parties. | N/A | Pattie L. To be confirmed

## Slide 9
Recap of Today's Discussion
1
Walkthrough the engagement scope and timelines
2
Review required documentation and key artifacts
4
Schedule recurring project touchpoints and meeting cadence
5
Complete Deloitte’s access request (SharePoint, Confluence, Teams)
6
Confirm contracting and engagement letter execution
3
Confirm stakeholder involvement and day-to-day points of contact
Complete
Complete
Complete
Deloitte to Schedule By?
Cynthia N. to complete the access request By?
Pattie L. To shared the signed CR back to Deloitte by?