## Admin
Admin Tracker
Open administrative / mobilization action items (access requests, contracting, scheduling, etc.)
Task | Beem Owner | Deloitte Owner | Due Date | Status | Notes
Everlink eAuthenticate and eDetect platform guides / processes. | Shikhar / Cynthia | Victoria | Sept 16th | In Progres | Sept 14: Vic to send email to Cynthia | Complete
Teams access for Victoria and Kass | Shikhar | David | Sept 25th | Not Started | Sept 14: David to send message to Shikhar once back from vacation on Sept 21 | In Progres
Not Started

## Fraud
Fraud Workstream — Project Plan
# | SOW Activity / Sub-Activity | Deloitte Owner | Beem Point of Contact | Start Date | End Date | Notes | Status | Req ID | Deliverables
1 | Design and document the end-to-end debit card fraud investigation operating model, including investigation workflows, decisioning criteria, escalation paths, alert disposition procedures, transaction review processes, and Visa’s first-party fraud governance. Deliver comprehensive Standard Operating Procedures (SOPs), process documentation, and investigator guidance materials to support ongoing fraud operations, across Everlink eDetect and eAuthenticate platforms. | Kass | Jesse Y. | 2026-09-08 | 2026-10-16 |  | In Progress
| Collect and review current enterprise fraud policies & current fraud investigation/case management process to identify potential gaps / changes | Kass | Jesse Y. | 2026-09-08 | 2026-09-15 | Docs Due Thu Sept 10 EOD | In Progress | N/A | 1. Summary table of all documents reviewed, proposed changes, and net-new processes to be created
| Collect and review Everlink eDetect and eAuthenticate documentation | Kass | Cynthia or Shikhar | 2026-09-14 | 2026-09-18 |  | In Progress | N/A | N/A - these documents will be embedded in the newly developed SOPs/processes
| Conduct working session with Beem to clarify current state understanding and align on identified changes | Kass | Jesse Y. | 2026-09-21 | 2026-09-21 |  | Not Started | N/A | N/A
| Draft Visa Debit Card Fraud Alert Investigation & Disposition SOP & Process Flow | Kass | Jesse Y. | 2026-09-22 | 2026-10-09 |  | Not Started | FD-01, FD-04, FD-13, FD-22 | 2. Visa Debit Card Fraud Alert Investigation & Disposition SOP & Process Flow (alert review in eDetect, investigation steps (review activity in eAuthenticate and other systems), member outreach, decisioning criteria, blocking of the card, card replacement, escalation path, SLAs)
| Draft Visa Debit Unauthorized Activity Customer Report Intake | Kass | Jesse Y. | 2026-09-22 | 2026-10-09 |  | Not Started | FD-01, FD-04, FD-22 | 3. Visa Debit Card Unauthorized Activity Customer Report Intake (report intake, initial triage, blocking of the card, card replacement, escalation to Fraud Team)
| Review current Fraud Policy and draft proposed Addendum (if applicable) | Kass | Jesse Y. | 2026-09-22 | 2026-10-09 |  | Not Started | N/A | 4. Beem Fraud Policy Addendum (How Visa Debit falls within the policy scope, roles and accountability, obligations and expectations)
| Draft eDetect data extration and retention process | Kass | Jesse Y. | 2026-10-12 | 2026-10-16 |  | Not Started | FD-23, FD-26 | 5. eDetect Data Extraction & Retention Process
| Conduct working session with Everlink to understand eDetect instance deployment timelines, proposed initial ruleset, reporting, data extraction | Kass | Jesse Y. | 2026-09-21 | 2026-10-02 |  | Not Started | FD-23, FD-21
| Review updated and newly created artifacts with Beem stakeholders and obtain final approval | Kass | Jesse Y. | 2026-10-19 | 2026-10-23 |  | Not Started | N/A
2 | Design DataVisor Visa debit fraud monitoring requirements, including data integration architecture, monitoring use cases, fraud detection rules, and governance considerations. | TBC | DataVisor Product Owner (TBC) / Jesse Y. | 2026-09-21 | 2026-10-16 |  | Not Started
| Collect and review DataVisor solution overview, design spec, and current data flow/architecture diagrams | TBC | Cynthia or Shikhar | 2026-09-21 | 2026-09-27 | Docs Due Thu Sept 10 EOD | In Progress | N/A | N/A
| Confirm DataVisor technical specifications and data source (DNA vs. Everlink) with Tech/Architecture stakeholders | TBC | Manoj | 2026-09-21 | 2026-09-25 |  | Not Started | N/A | N/A
| Draft DataVisor Data Integration Architecture & Requirements | TBC | Jesse Y. | 2026-09-28 | 2026-10-02 |  | Not Started | FD-02 | 1. DataVisor Data Integration Architecture & Requirements
| Draft DataVisor Fraud Monitoring Use Cases & Detection/Alerting Rules | TBC | Jesse Y. | 2026-10-02 | 2026-10-07 |  | Not Started | FD-02, FD-03 | 2. DataVisor Fraud Monitoring Use Cases & Detection/Alerting Rules
| Draft DataVisor Governance & Oversight Considerations | TBC | Jesse Y. | 2026-10-07 | 2026-10-09 |  | Not Started | N/A | 3. DataVisor Governance & Oversight Considerations
| Review & finalize requirements document with stakeholders | TBC | Jesse Y. | 2026-10-12 | 2026-10-16 |  | Not Started | N/A
3 | Develop a comprehensive integration and transition roadmap for the migration of fraud monitoring capabilities from Everlink to DataVisor following Visa Debit launch. The roadmap will include data integration requirements, operating model impacts, implementation sequencing, testing and validation activities, cutover considerations, risk mitigation strategies, and transition governance to support a seamless migration to the future-state platform. | TBC | Shikhar / David / Cynthia (TBC); Manoj (technical) | 2026-10-19 | 2026-11-20 |  | Not Started
| Confirm technical specifications and integration touchpoints with Manoj | TBC | Manoj | 2026-10-19 | 2026-10-23 |  | Not Started | N/A | N/A
| Assess data integration requirements & operating model impacts (DNA / Everlink / DataVisor) | TBC | Shikhar/David/Cynthia | 2026-10-26 | 2026-10-30 |  | Not Started | N/A | 1. Data Integration Requirements & Operating Model Impact Assessment
| Draft implementation sequencing, testing & validation plan | TBC | Shikhar/David/Cynthia | 2026-11-02 | 2026-11-09 |  | Not Started | N/A | 2. Everlink -> DataVisor Implementation Sequencing & Testing/Validation Plan
| Draft cutover plan, transition governance approach & risk mitigation strategies | TBC | Shikhar/David/Cynthia | 2026-11-09 | 2026-11-13 |  | Not Started | N/A | 3. Everlink -> DataVisor Cutover, Transition Governance & Risk Mitigation Plan
| Review & finalize roadmap with stakeholders | TBC | Shikhar/David/Cynthia | 2026-11-16 | 2026-11-20 |  | Not Started | N/A
4 | Develop an analytics-driven fraud detection process to identify emerging fraud trends and anomalies based on authentication failure patterns. | TBC | Jesse Y. | 2026-11-09 | 2026-12-11 |  | Not Started
| Define authentication-failure-pattern analysis approach (net-new; no existing Beem documentation required) | TBC | Jesse Y. | 2026-11-09 | 2026-11-13 |  | Not Started | N/A | N/A
| Draft analytics-driven fraud detection methodology | TBC | Jesse Y. | 2026-11-16 | 2026-12-04 |  | Not Started | FD-15 | 1. Analytics-Driven Fraud Detection Process (authentication failure pattern analysis methodology)
| Review & finalize with stakeholders | TBC | Jesse Y. | 2026-12-07 | 2026-12-11 |  | Not Started | N/A
5 | Design and implement an internal fraud reporting framework, including fraud loss reporting, Visa threshold monitoring, management reporting, and Sponsor Bank and Visa reporting processes. | TBC | Jesse Y. | 2026-11-23 | 2026-12-11 |  | Not Started
| Collect and review current fraud loss reporting/dashboards & reporting cadence/formats | TBC | Jesse Y. | 2026-11-23 | 2026-11-25 |  | Not Started | N/A | N/A
| Draft Internal Fraud Reporting Framework (fraud loss reporting, VIMP threshold monitoring, management reporting) | TBC | Jesse Y. | 2026-11-25 | 2026-12-02 |  | Not Started | FD-19, FD-20 | 1. Internal Fraud Reporting Framework (fraud loss reporting, VIMP threshold monitoring, management reporting)
| Draft Visa Fraud Reporting System (FRS) Submission Process | TBC | Jesse Y. | 2026-12-02 | 2026-12-04 |  | Not Started | FD-11 | 2. Visa Fraud Reporting System (FRS) Submission Process
| Draft ICICI Sponsor Bank Fraud Reporting Process | TBC | Jesse Y. | 2026-12-04 | 2026-12-07 |  | Not Started | FD-12 | 3. ICICI Sponsor Bank Fraud Reporting Process
| Review & finalize with stakeholders | TBC | Jesse Y. | 2026-12-07 | 2026-12-11 |  | Not Started | N/A
| Completion of Fraud Transformation Activities |  |  |  | 2026-12-11

## AML
AML Workstream — Project Plan
# | SOW Activity / Sub-Activity | Deloitte Owner | Beem Point of Contact | Start Date | End Date | Notes | Status | Req ID | Deliverables
6 | Review and enhance the AML framework to support Visa Debit products and services, including policies, procedures, governance controls, sanctions screening requirements, investigation processes, regulatory, Sponsor Bank and Visa reporting obligations. | TBC | Sandra M. | 2026-09-10 | 2026-10-16 |  | In Progress
| Collect and review current AML policy & current AML alert, case, and regulatory reporting processes to identify potential gaps / changes | TBC | Sandra M. | 2026-09-10 | 2026-09-16 | Due Thu Sept 10 EOD | In Progress | N/A | N/A
| Conduct working sessions with AML team to validate and clarify understanding of AML framework and align on proposed gaps / changes | TBC | Sandra M. | 2026-09-14 | 2026-09-21 |  | Not Started | N/A | N/A
| Draft enhanced AML policies, procedures & governance controls | TBC | Sandra M. | 2026-09-21 | 2026-09-25 |  | Not Started | AML-01 | 1. Enhanced AML Policies, Procedures & Governance Controls (Visa Debit)
| Draft sanctions screening process & requirements | TBC | Sandra M. | 2026-09-25 | 2026-09-29 |  | Not Started | AML-03, AML-05 | 2. Sanctions Screening Process & Requirements (OFAC SDN screening, true-match card/account disablement)
| Draft AML investigation & case management process | TBC | Sandra M. | 2026-09-29 | 2026-10-05 |  | Not Started | AML-01 | 3. AML Investigation & Case Management Process
| Draft regulatory, Sponsor Bank & Visa reporting requirements (FINTRAC, ICICI) | TBC | Sandra M. | 2026-10-05 | 2026-10-09 |  | Not Started | AML-06, AML-07, AML-08 | 4. AML Regulatory & Sponsor Bank Reporting Requirements (FINTRAC STR/EFT/LCT, ICICI)
| Review & finalize with Beem stakeholders | TBC | Sandra M. | 2026-10-12 | 2026-10-16 |  | Not Started | N/A
7 | Design, build and operationalize the AML monitoring framework for Visa Debit activity, including monitoring methodologies, monitoring rules, alert scenarios, testing, and production readiness activities. | TBC | Sandra M.; Navaera Relationship Owner (TBC) | 2026-09-28 | 2026-11-06 |  | Not Started
| Beem to introduce Deloitte to Navaera to discuss PCI-compliance workaround | TBC | Sandra M. / Navaera Relationship Owner (TBC) | 2026-09-28 | 2026-10-02 | Kwaseem from Navaera to coordinate time | Not Started | N/A | N/A
| Assess whether Navaera's workaround is sufficient; confirm build approach | TBC | Sandra M. | 2026-09-28 | 2026-10-02 |  | Not Started | N/A | N/A
| Draft AML monitoring methodology & risk coverage approach | TBC | Sandra M. | 2026-10-05 | 2026-10-09 |  | Not Started | N/A | 1. AML Monitoring Methodology & Risk Coverage Approach
| Draft AML monitoring rules & alert scenarios | TBC | Sandra M. | 2026-10-09 | 2026-10-16 |  | Not Started | AML-11 | 2. AML Monitoring Rules & Alert Scenarios
| Conduct testing & validation of AML monitoring rules | TBC | Sandra M. | 2026-10-19 | 2026-10-25 |  | Not Started | AML-12 | 3. AML Monitoring Rules Testing & Validation Summary
| Complete production readiness & operationalization activities | TBC | Sandra M. | 2026-10-26 | 2026-10-30 |  | Not Started | AML-12, AML-13 | 4. AML Monitoring Production Readiness & Operationalization Checklist
| Review & finalize with Beem stakeholders | TBC | Sandra M. | 2026-11-02 | 2026-11-06 |  | Not Started | N/A
8 | Design and implement an internal AML reporting framework, including operational and analytics performance reports. | TBC | Sandra M. | 2026-11-09 | 2026-11-27 |  | Not Started
| Collect current AML reports/dashboards & reporting cadence/formats | TBC | Sandra M. | 2026-11-09 | 2026-11-11 |  | Not Started | N/A | N/A
| Draft internal AML reporting framework (operational & analytics performance reports) | TBC | Sandra M. | 2026-11-12 | 2026-11-20 |  | Not Started | AML-09 | 1. Internal AML Reporting Framework (operational & analytics performance reports)
| Review & finalize with stakeholders | TBC | Sandra M. | 2026-11-23 | 2026-11-27 |  | Not Started | N/A
| Completion of AML Transformation Activities |  |  |  | 2026-11-27

## Dispute Resolution
Dispute Resolution Workstream — Project Plan
# | SOW Activity / Sub-Activity | Deloitte Owner | Beem Point of Contact | Start Date | End Date | Notes | Status | Req ID | Deliverables
9 | Design and document the end-to-end dispute management lifecycle, including dispute intake, fraud or non-fraud determination, provisional credit issuance, chargeback submission (via Central 1), Visa dispute processing, and funds recovery activities. Deliver supporting procedures, process maps, and operational controls to support efficient dispute resolution and recovery operations. | TBC | Loni B. (Non-fraud Disputes); Pattie L. (Fraudulent Disputes) | 2026-09-14 | 2026-10-16 |  | Not Started
| Draft target-state dispute intake & fraud/non-fraud determination process | TBC | Loni B. / Pattie L. | 2026-09-14 | 2026-09-22 |  | Not Started | FD-06 | 1. Target-State Dispute Intake & Fraud/Non-Fraud Determination Process
| Draft target-state provisional credit, chargeback submission (Central 1) & Visa dispute processing flow | TBC | Loni B. / Pattie L. | 2026-09-22 | 2026-09-30 |  | Not Started | FD-09 | 2. Target-State Provisional Credit, Chargeback (Central 1) & Visa Dispute Processing Flow
| Draft target-state funds recovery process & supporting procedures/process maps | TBC | Loni B. / Pattie L. | 2026-09-30 | 2026-10-16 |  | Not Started | FD-10 | 3. Target-State Funds Recovery Process & Supporting Procedures/Process Maps
10 | Refine / Finalize Target-State Process | TBC | Loni B. (Non-fraud Disputes); Pattie L. (Fraudulent Disputes) | 2026-10-12 | 2026-11-20 |  | Not Started
| Collect and review current dispute policies/process (incl. Central 1) & current dispute forms/templates/comms | TBC | Loni B. / Pattie L. | 2026-10-12 | 2026-10-16 |  | Not Started | N/A | N/A
| Compare target-state design against Beem's current-state dispute process | TBC | Loni B. / Pattie L. | 2026-10-19 | 2026-11-13 |  | Not Started | N/A | 1. Target-State vs. Current-State Dispute Process Gap Analysis
| Conduct review sessions with Loni B. and Pattie L. | TBC | Loni B. / Pattie L. | 2026-10-19 | 2026-11-13 |  | Not Started | N/A | N/A
| Incorporate feedback & finalize process maps and operational controls, including first-party dispute monitoring & review process | TBC | Loni B. / Pattie L. | 2026-11-16 | 2026-11-20 |  | Not Started | FD-06, FD-07, FD-08, FD-10 | 2. Finalized Target-State Dispute Management Process, SOPs & Process Maps (incl. first-party dispute monitoring & review)
| Completion of Dispute Resolution Transformation Activities |  |  |  | 2026-11-20

## TPRM & Oversight
TPRM & Oversight Workstream — Project Plan
# | SOW Activity / Sub-Activity | Deloitte Owner | Beem Point of Contact | Start Date | End Date | Notes | Status | Req ID | Deliverables
11 | Review and enhance existing third-party risk management processes to incorporate Visa Debit and BIN Sponsorship requirements, ensuring vendor oversight activities align with applicable regulatory, network, and contractual obligations. | TBC | Akinwale A. | 2026-10-26 | 2026-11-13 |  | Not Started
| Collect and assess current TPRM policies & processes against Visa Debit & BIN Sponsorship requirements | TBC | Akinwale A. | 2026-10-26 | 2026-10-30 |  | Not Started | N/A | N/A
| Draft enhanced TPA contracting review process & controls (Visa-mandated clauses) | TBC | Akinwale A. | 2026-11-02 | 2026-11-04 |  | Not Started | TPA-01 | 1. Enhanced TPA Contracting Review Process (Visa-mandated clause checklist)
| Draft enhanced TPA due diligence process & controls | TBC | Akinwale A. | 2026-11-04 | 2026-11-06 |  | Not Started | TPA-02 | 2. Enhanced TPA Due Diligence Process & Controls
| Draft TPA relationship change / Sponsor Bank notification process | TBC | Akinwale A. | 2026-11-06 | 2026-11-09 |  | Not Started | TPA-03 | 3. TPA Relationship Change & Sponsor Bank Notification Process
| Review & finalize with Akinwale A. | TBC | Akinwale A. | 2026-11-09 | 2026-11-13 |  | Not Started | N/A
12 | Establish process to submit annual Attestation of Compliance to ICICI Bank. | TBC | Akinwale A. | 2026-11-16 | 2026-11-27 |  | Not Started
| Collect and review excerpt of ICICI contract (attestation requirements, templates, submission guidance) | TBC | Akinwale A. | 2026-11-16 | 2026-11-18 |  | Not Started | N/A | N/A
| Draft annual ICICI Attestation of Compliance submission process | TBC | Akinwale A. | 2026-11-19 | 2026-11-23 |  | Not Started | OS-04 | 1. Annual ICICI Attestation of Compliance Submission Process
| Review & finalize with Akinwale A. / Pattie L. | TBC | Akinwale A. | 2026-11-24 | 2026-11-27 |  | Not Started | N/A
13 | Design and implement a centralized artifact repository and communication framework to support Visa Debit oversight activities, including storage and management of policies, procedures, reporting artifacts, compliance evidence, governance documentation, issue logs, and correspondence with regulators, Visa, and 3rd parties. | TBC | Akinwale A. | 2026-11-30 | 2026-12-11 |  | Not Started
| Design repository structure & communication framework - working session with Akinwale to align on structure | TBC | Akinwale A. | 2026-11-30 | 2026-12-04 | N/A - no doc needed | Not Started | N/A | N/A
| Configure & populate repository (policies, procedures, reporting artifacts, compliance evidence, governance docs, issue logs) to support ongoing compliance monitoring | TBC | Akinwale A. | 2026-12-07 | 2026-12-09 |  | Not Started | OS-01, OS-03 | 1. Centralized Artifact Repository (policies, procedures, reporting artifacts, compliance evidence, governance docs, issue logs)
| Build communication framework for regulator / Visa / third-party correspondence | TBC | Akinwale A. | 2026-12-09 | 2026-12-11 |  | Not Started | OS-02 | 2. Oversight Communication Framework (regulator, Visa & third-party correspondence)
| Review & hand over to Beem | TBC | Akinwale A. | 2026-12-07 | 2026-12-11 |  | Not Started | N/A
| Completion of TPRM & Oversight Transformation Activities |  |  |  | 2026-12-11