## Admin Tracker
Admin Tracker
Open administrative / mobilization action items (access requests, contracting, scheduling, etc.)
Task | Beem Owner | Deloitte Owner | Due Date | Notes
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Governance - schedule meeting, doc request,

## Fraud
Fraud Workstream — Project Plan
# | Activity / Sub-Activity | Type | Owner | Point of Contact | Start Date | End Date | Notes | Status |  | Deliverables
1 | Design and Document Fraud Investigation Operating Model & Process | Activity | Deloitte | Jesse Y. | 2026-09-08 | 2026-10-16 |  | Not Started |  | 1. Debit Card Fraud Investigation Operating Model 2. Investigation SOPs to support fraud operations across Everlink eDetect and eAuthenticate platforms
| Collect and review current enterprise fraud policies & current fraud investigation/case management process | Sub-Activity | Beem | Jesse Y. | 2026-09-08 | 2026-09-15 | Docs Due Thu Sept 10 EOD | In Progress | Design and document the end-to-end debit card fraud investigation operating model, including investigation workflows, decisioning criteria, escalation paths, alert disposition procedures, transaction review processes, and Visa’s first-party fraud governance. Deliver comprehensive Standard Operating Procedures (SOPs), process documentation, and investigator guidance materials to support ongoing fraud operations, across Everlink eDetect and eAuthenticate platforms.
| Conduct working sessions on investigation workflows, decisioning criteria & escalation paths to validate and clarify current state understanding | Sub-Activity | Deloitte | Jesse Y. | 2026-09-16 | 2026-10-09 |  | Not Started
| Draft fraud investigation operating model & SOPs (incl. eDetect & eAuthenticate) | Sub-Activity | Deloitte | Jesse Y. | 2026-09-16 | 2026-10-09 |  | Not Started
| Review & finalize SOPs with Beem stakeholders | Sub-Activity | Joint | Jesse Y. | 2026-10-12 | 2026-10-16 |  | Not Started
2 | Design DataVisor Monitoring Requirements | Activity | Deloitte | DataVisor Product Owner (TBC) / Jesse Y. | 2026-09-21 | 2026-10-16 |  | Not Started |  | 1. DataVisor Visa Debit Fraud Monitoring Requirements (data integration architecture, monitoring use cases) 2. DataVisor Fraud Detection Rules & Governance Considerations
| Obtain and review DataVisor solution overview, design spec & current data flow/architecture diagrams | Sub-Activity | Beem | Cynthia or Shikhar | 2026-09-21 | 2026-09-27 | Docs Due Thu Sept 10 EOD | In Progress | Design DataVisor Visa debit fraud monitoring requirements, including data integration architecture, monitoring use cases, fraud detection rules, and governance considerations.
| Confirm DataVisor technical sepcifications and data source (DNA vs. Everlink) with Tech/Architecture stakeholders | Sub-Activity | Joint | Manoj | 2026-09-21 | 2026-09-25 |  | Not Started
| Draft monitoring use cases, detection rules & governance requirements | Sub-Activity | Deloitte | Jesse Y. | 2026-09-28 | 2026-10-09 |  | Not Started
| Review & finalize with stakeholders | Sub-Activity | Joint | Jesse Y. | 2026-10-12 | 2026-10-16 |  | Not Started
3 | Develop Everlink -> DataVisor Transition Roadmap | Activity | Deloitte | Shikhar / David / Cynthia (TBC); Manoj (technical) | 2026-10-19 | 2026-11-20 |  | Not Started |  | 1. Everlink -> DataVisor Integration & Transition Roadmap
| Assess data integration requirements & operating model impacts | Sub-Activity | Deloitte | Shikhar/David/Cynthia | 2026-10-19 | 2026-10-30 |  | Not Started | Develop a comprehensive integration and transition roadmap for the migration of fraud monitoring capabilities from Everlink to DataVisor following Visa Debit launch. The roadmap will include data integration requirements, operating model impacts, implementation sequencing, testing and validation activities, cutover considerations, risk mitigation strategies, and transition governance to support a seamless migration to the future-state platform.
| Draft implementation requirements, sequencing of activities, testing/validation & cutover plan | Sub-Activity | Deloitte | Shikhar/David/Cynthia | 2026-11-02 | 2026-11-13 |  | Not Started
| Review & finalize roadmap with stakeholders | Sub-Activity | Joint | Shikhar/David/Cynthia | 2026-11-16 | 2026-11-20 |  | Not Started
4 | Develop Analytics-driven Fraud Detection Process | Activity | Deloitte | Jesse Y. | 2026-11-09 | 2026-12-11 |  | Not Started |  | 1. Analytics-Driven Fraud Detection Process (authentication failure pattern analysis)
| Define authentication-failure-pattern analysis approach (net-new; no existing docs required) | Sub-Activity | Deloitte | Jesse Y. | 2026-11-09 | 2026-11-13 |  | Not Started | Develop an analytics-driven fraud detection process to identify emerging fraud trends and anomalies based on authentication failure patterns.
| Draft analytics-driven detection methodology | Sub-Activity | Deloitte | Jesse Y. | 2026-11-16 | 2026-12-04 |  | Not Started
| Review & finalize with stakeholders | Sub-Activity | Joint | Jesse Y. | 2026-12-07 | 2026-12-11 |  | Not Started
5 | Update Fraud Reporting Process | Activity | Deloitte | Jesse Y. | 2026-11-23 | 2026-12-11 |  | Not Started |  | 1. Internal Fraud Reporting Framework 2. Fraud Loss & Visa Threshold Monitoring Reporting Templates (management, Sponsor Bank & Visa reporting)
| Collect and review current fraud loss reporting/dashboards & reporting cadence/formats | Sub-Activity | Beem | Jesse Y. | 2026-11-23 | 2026-11-25 |  | Not Started | Design and implement an internal fraud reporting framework, including fraud loss reporting, Visa threshold monitoring, management reporting, and Sponsor Bank and Visa reporting processes.
| Draft updated fraud reporting framework (loss reporting, VIMP thresholds, mgmt reporting, Sponsor Bank & Visa reporting) | Sub-Activity | Deloitte | Jesse Y. | 2026-11-25 | 2026-12-04 |  | Not Started
| Review & finalize with stakeholders | Sub-Activity | Joint | Jesse Y. | 2026-12-07 | 2026-12-11 |  | Not Started
| Completion of Fraud Transformation Activities | Milestone | Joint |  |  | 2026-12-11 |  | Not Started

## AML
AML Workstream — Project Plan
# | Activity / Sub-Activity | Type | Owner | Point of Contact | Start Date | End Date | Notes | Status |  | Deliverables
6 | Review the Current AML Process and Policy | Activity | Deloitte | Sandra M. | 2026-09-10 | 2026-10-16 |  | Not Started |  | 1. Enhanced AML Framework for Visa Debit (policies, procedures, governance controls, sanctions screening, investigation processes)
| Collect and review current AML policy & current AML alert, case, and regulatory reporting processes | Sub-Activity | Beem | Sandra M. | 2026-09-10 | 2026-09-16 | Due Thu Sept 10 EOD | In Progress | Review and enhance the AML framework to support Visa Debit products and services, including policies, procedures, governance controls, sanctions screening requirements, investigation processes, regulatory, Sponsor Bank and Visa reporting obligations.
| Conduct working sessions with AML team to validate and clarify understanding of AML framework (policies, governance controls, sanctions screening, investigation processes) | Sub-Activity | Deloitte | Sandra M. | 2026-09-14 | 2026-10-09 |  | Not Started
| Draft enhanced AML framework (policies, governance controls, sanctions screening, investigation processes) | Sub-Activity | Deloitte | Sandra M. | 2026-09-14 | 2026-10-09 |  | Not Started
| Review & finalize with Beem stakeholders | Sub-Activity | Joint | Sandra M. | 2026-10-12 | 2026-10-16 |  | Not Started
7 | Update the AML Monitoring Process | Activity | Deloitte | Sandra M.; Navaera Relationship Owner (TBC) | 2026-09-28 | 2026-11-06 |  | Not Started |  | 1. AML Monitoring Framework for Visa Debit Activity (methodologies, monitoring rules, alert scenarios) 2. Testing & Production Readiness Documentation
| Beem to introduce Deloitte to Navaera to discuss PCI-compliance workaround | Sub-Activity | Beem | Sandra M. / Navaera Relationship Owner (TBC) | 2026-09-28 | 2026-10-02 | Kwaseem from Navaera to coordinate time | Not Started | Design, build and operationalize the AML monitoring framework for Visa Debit activity, including monitoring methodologies, monitoring rules, alert scenarios, testing, and production readiness activities.
| Assess whether Navaera's workaround is sufficient; confirm build approach | Sub-Activity | Joint | Sandra M. | 2026-09-28 | 2026-10-02 |  | Not Started
| Design monitoring methodologies, monitoring rules & alert scenarios | Sub-Activity | Deloitte | Sandra M. | 2026-10-05 | 2026-10-16 |  | Not Started
| Testing & production readiness activities | Sub-Activity | Deloitte | Sandra M. | 2026-10-19 | 2026-10-30 |  | Not Started
| Review & finalize with Beem stakeholders | Sub-Activity | Deloitte | Sandra M. | 2026-11-02 | 2026-11-06 |  | Not Started
8 | Update AML Reporting Process | Activity | Deloitte | Sandra M. | 2026-11-09 | 2026-11-27 |  | Not Started |  | 1. Internal AML Reporting Framework (operational & analytics performance reports)
| Collect current AML reports/dashboards & reporting cadence/formats | Sub-Activity | Beem | Sandra M. | 2026-11-09 | 2026-11-11 |  | Not Started | Design and implement an internal AML reporting framework, including operational and analytics performance reports.
| Draft internal AML reporting framework (operational & analytics performance reports) | Sub-Activity | Deloitte | Sandra M. | 2026-11-12 | 2026-11-20 |  | Not Started
| Review & finalize with stakeholders | Sub-Activity | Joint | Sandra M. | 2026-11-23 | 2026-11-27 |  | Not Started
| Completion of AML Transformation Activities | Milestone | Joint |  |  | 2026-11-27 |  | Not Started

## Dispute Resolution
Dispute Resolution Workstream — Project Plan
# | Activity / Sub-Activity | Type | Owner | Point of Contact | Start Date | End Date | Notes | Status |  | Deliverables
9 | Build Target-state Dispute Management Process | Activity | Deloitte | Loni B. (Non-fraud Disputes); Pattie L. (Fraudulent Disputes) | 2026-09-14 | 2026-10-16 |  | Not Started |  | 1. Target-State Dispute Management Lifecycle Design 2. Supporting Dispute Procedures, Process Maps & Operational Controls
| Design target-state dispute lifecycle (intake, fraud/non-fraud determination, provisional credit, chargeback via Central 1, Visa processing, funds recovery) | Sub-Activity | Deloitte | Loni B. / Pattie L. | 2026-09-14 | 2026-10-16 |  | Not Started | Design and document the end-to-end dispute management lifecycle, including dispute intake, fraud or non-fraud determination, provisional credit issuance (see out of scope activity #1), chargeback submission (via Central 1), Visa dispute processing, and funds recovery activities. Deliver supporting procedures, process maps, and operational controls to support efficient dispute resolution and recovery operations.
10 | Refine / Finalize Target-State Process | Activity | Joint | Loni B. (Non-fraud Disputes); Pattie L. (Fraudulent Disputes) | 2026-10-12 | 2026-11-20 |  | Not Started |  | 1. Finalized, Beem-Approved Target-State Dispute Management Process
| Collect and review current dispute policies/process (incl. Central 1) & current dispute forms/templates/comms | Sub-Activity | Beem | Loni B. / Pattie L. | 2026-10-12 | 2026-10-16 |  | Not Started
| Compare target-state design against Beem's current-state dispute process | Sub-Activity | Deloitte | Loni B. / Pattie L. | 2026-10-19 | 2026-11-13 |  | Not Started
| Conduct review sessions with Loni B. and Pattie L. | Sub-Activity | Joint | Loni B. / Pattie L. | 2026-10-19 | 2026-11-13 |  | Not Started
| Incorporate feedback & finalize process maps and operational controls | Sub-Activity | Deloitte | Loni B. / Pattie L. | 2026-11-16 | 2026-11-20 |  | Not Started
| Completion of Dispute Resolution Transformation Activities | Milestone | Joint |  |  | 2026-11-20 |  | Not Started

## TPRM & Oversight
TPRM & Oversight Workstream — Project Plan
# | Activity / Sub-Activity | Type | Owner | Point of Contact | Start Date | End Date | Notes | Status |  | Deliverables
11 | Enhance Existing TPRM Process | Activity | Deloitte | Akinwale A. | 2026-10-26 | 2026-11-13 |  | Not Started |  | 1. Enhanced TPRM Process & Procedures (Visa Debit & BIN Sponsorship requirements)
| Collect and assess current process against Visa Debit & BIN Sponsorship requirements current TPRM policies & processes | Sub-Activity | Beem | Akinwale A. | 2026-10-26 | 2026-10-30 |  | Not Started | Review and and enhance existing third-party risk management processes to incorporate Visa Debit and BIN Sponsorship requirements, ensuring vendor oversight activities align with applicable regulatory, network, and contractual obligations.
| Draft enhanced TPRM process & controls | Sub-Activity | Deloitte | Akinwale A. | 2026-11-02 | 2026-11-06 |  | Not Started
| Review & finalize with Akinwale A. | Sub-Activity | Joint | Akinwale A. | 2026-11-09 | 2026-11-13 |  | Not Started
12 | Establish ICICI Attestation Process | Activity | Deloitte | Akinwale A. | 2026-11-16 | 2026-11-27 |  | Not Started |  | 1. Annual ICICI Attestation of Compliance Submission Process
| Collect and review excerpt of ICICI contract (attestation requirements, templates, submission guidance) | Sub-Activity | Beem | Akinwale A. | 2026-11-16 | 2026-11-18 |  | Not Started | Establish process to submit annual Attestation of Compliance to ICICI Bank.
| Draft annual Attestation of Compliance submission process | Sub-Activity | Deloitte | Akinwale A. | 2026-11-19 | 2026-11-23 |  | Not Started
| Review & finalize with Akinwale A. / Pattie L. | Sub-Activity | Joint | Akinwale A. | 2026-11-24 | 2026-11-27 |  | Not Started
13 | Build Centralized Artifact Repository | Activity | Deloitte | Akinwale A. | 2026-11-30 | 2026-12-11 |  | Not Started |  | 1. Centralized Artifact Repository (policies, procedures, reporting artifacts, compliance evidence, governance docs, issue logs) 2. Oversight Communication Framework (regulator, Visa & third-party correspondence)
| Design repository structure & communication framework - Working Sessions with Akinwale to align on structure | Sub-Activity | Deloitte | Akinwale A. | 2026-11-30 | 2026-12-04 | N/A - no doc needed | Not Started | Design and implement a centralized artifact repository and communication framework to support Visa Debit oversight activities, including storage and management of policies, procedures, reporting artifacts, compliance evidence, governance documentation, issue logs, and correspondence with regulators, Visa, and 3rd parties.
| Configure & populate repository (policies, procedures, reporting artifacts, compliance evidence, governance docs, issue logs) | Sub-Activity | Deloitte | Akinwale A. | 2026-12-07 | 2026-12-11 |  | Not Started
| Review & hand over to Beem | Sub-Activity | Joint | Akinwale A. | 2026-12-07 | 2026-12-11 |  | Not Started
| Completion of TPRM & Oversight Transformation Activities | Milestone | Joint |  |  | 2026-12-11 |  | Not Started

## Consolidated - High Level
Visa Debit Transformation Phase — Consolidated Project Plan
14-Week Engagement · Sept 8 – Dec 11, 2026 · High-level view across all workstreams (activity-level; see individual tabs for sub-activities)
Workstream | # | Activity | Owner | Point of Contact | Start Date | End Date | Status
All |  | Ongoing Project Management (Weekly Status Update) | Deloitte | Engagement Lead | 2026-09-08 | 2026-12-11 | Ongoing
Fraud | 1 | Design and Document Fraud Investigation Operating Model & Process | Deloitte | Jesse Y. |  |  | Not Started
Fraud | 2 | Design DataVisor Monitoring Requirements | Deloitte | DataVisor Product Owner (TBC) / Jesse Y. |  |  | Not Started
Fraud | 3 | Develop Everlink -> DataVisor Transition Roadmap | Deloitte | Shikhar / David / Cynthia (TBC); Manoj (technical) |  |  | Not Started
Fraud | 4 | Develop Analytics-driven Fraud Detection Process | Deloitte | Jesse Y. |  |  | Not Started
Fraud | 5 | Update Fraud Reporting Process | Deloitte | Jesse Y. |  |  | Not Started
Fraud |  | Completion of Fraud Transformation Activities | Joint |  |  | 2026-12-11 | Not Started
AML | 6 | Review the Current AML Process and Policy | Deloitte | Sandra M. |  |  | Not Started
AML | 7 | Update the AML Monitoring Process | Deloitte | Sandra M.; Navaera Relationship Owner (TBC) |  |  | Not Started
AML | 8 | Update AML Reporting Process | Deloitte | Sandra M. |  |  | Not Started
AML |  | Completion of AML Transformation Activities | Joint |  |  | 2026-11-27 | Not Started
Dispute Resolution | 9 | Build Target-state Dispute Management Process | Deloitte | Loni B. (Non-fraud Disputes); Pattie L. (Fraudulent Disputes) |  |  | Not Started
Dispute Resolution | 10 | Refine / Finalize Target-State Process | Joint | Loni B. (Non-fraud Disputes); Pattie L. (Fraudulent Disputes) |  |  | Not Started
Dispute Resolution |  | Completion of Dispute Resolution Transformation Activities | Joint |  |  | 2026-11-20 | Not Started
TPRM & Oversight | 11 | Enhance Existing TPRM Process | Deloitte | Akinwale A. |  |  | Not Started
TPRM & Oversight | 12 | Establish ICICI Attestation Process | Deloitte | Akinwale A. |  |  | Not Started
TPRM & Oversight | 13 | Build Centralized Artifact Repository | Deloitte | Akinwale A. |  |  | Not Started
TPRM & Oversight |  | Completion of TPRM & Oversight Transformation Activities | Joint |  |  | 2026-12-11 | Not Started